## Typical Accreditation Timeline
Typical Accreditation Timeline

## Data
Data
Task | Start month | Number of Months to complete
Unit introduced to QMS (internal auditing, non-conforming work, management review etc.) | 0 | 3
Unit fully engaged with QMS | 3 | 2
Method development/develop SOPs | 3 | 2
Undertake training and competence assessments | 5 | 2
Complete validation(s) | 7 | 4
Finalise method(s)/SOPs | 11 | 1
Undertake training/competency for remainder of staff | 12 | 4
Conduct proficiency testing/ILC | 12 | 3
‘Steady state’ prior to UKAS assessment (as a minimum) | 12 | 3
UKAS Assessment – positive recommendation | 15 | 0.25
Evidence submission | 15 | 3
UKAS review of evidence | 18 | 1
Further evidence submission | 19 | 1
UKAS review of further evidence | 20 | 1
Second round of further evidence submission | 21 | 1
UKAS review of second round of further evidence | 22 | 1
Granting of accreditation | 23 | 0.2

## Document Control
Document Control
Document Title: | Typical Accreditation Timeline
Reference | FCN-QP-MGT-REF-0005 | FCN Pillar | Quality
Version: | 1 | Document Owner: | Quality Specailist
Issue Date: | 2022-02-23 | Approved by: | Jane D'Arcy
UNCONTROLLED WHEN PRINTED OR ELECTRONICALLY SHARED OUTSIDE THE FCN
Please always refer to the FCN Quality Management System for latest versions
OFFICIAL
Document status | Approved
Author | James Kendall-Milnes
Reviewed By | Di Toyne
Update History
Version | Reason for Issue | Issue Date | Updated by
1 | New document | 2022-02-23 | James Kendall-Milnes